## Production Plan with Examples
Category | Priority (1-5) | Task | Date Added | Assigned To | High Est (In Hours) | Low Est (In Hours) | Actual Time (When Done) | Status | Notes
Art | 1 | Player sprites | 2018-04-25 | Aaron | 4 | 2 |  | In Progress
Art | 1 | Guard sprites | 2018-04-25 | Aaron | 4 | 2 |  | Not Done
Art | 2 | Entry Door | 2018-04-25 | Aaron | 2 | 0.5 |  | Not Done
Art | 2 | Exit Door | 2018-04-25 | Aaron | 2 | 0.5 |  | Not Done
Art | 3 | Floor (Background) | 2018-04-25 | Aaron | 1 | 0.5 | 2 | Done
Art | 1 | Wall Set | 2018-04-25 | Aaron | 8 | 5 |  | Not Done
Art | 4 | Misc. Animations | 2018-04-25 | Aaron | 6 | 4 |  | Postponed | Will write more detail and be more specific in next sprint, Too much art to do in this sprint
Design | 1 | Bank Level floorplan | 2018-04-25 | Alex |  |  |  | Not Done
Design | 1 | Museum Level floorplan | 2018-04-25 | Evelyn |  |  |  | Not Done
Design | 1 | Temple Level floorplan | 2018-04-25 | Aaron | 2 | 0.5 |  | Not Done
Design | 1 | StoryBoard for Game | 2018-04-25 | Aaron | 3 | 1 |  | Done | turned in
Programming | 2 | Cone of vision | 2018-04-25 | Alex, Evelyn | 6 | 3 |  | Done | works but may need tuning
Programming | 2 | Guard AI | 2018-04-25 | Alex |  |  |  | Not Done | guard randomly wonders and chases player when spotted
Design | 1 | Tutorial Level floorplan | 2018-04-25 | All | 2 | 1 |  | Done | same as our paper prototype
Programming | 3 | Movable Walls and Collision | 2018-04-25 | Alex, Evelyn | 4 | 2 |  | Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
Not Done
|  | HIGH |  | 44 | < Total High Est Column
|  | LOW |  | 22 | < Total Low Est Column
|  | AVERAGE |  | 33 | < Average of Total High and Total Low
|  | DONE |  | 2 | < Total Actual Time Column
|  | REMAINING |  | 31 | < AVERAGE - DONE
Graveyard of Cut Features

## Burn Down With Examples
This template credited to: Adrian Fittolani
Sprint Data
Team members | 3 | < number of team members
Hours per day | 3 | < how many hours each member agrees to contribute to the project each day
Days | 10 | < number of days in sprint
Burn Down
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task Hrs | 150 | 150 | 137 | 100 | 100 | 100 | 80 | 80 | 40 | 10 | <manually updated from total remaining time
Available Hrs | 162 | 145.8 | 129.6 | 113.4 | 97.2 | 81 | 64.8 | 48.6 | 32.4 | 16.2 | <automatically generated from C3*C4*C5

## Burn Down Clean Template
This template credited to: Adrian Fittolani
Sprint Data
Team members | 3 | < number of team members
Hours per day |  | < how many hours each member agrees to contribute to the project each day
Days | 10 | < number of days in sprint,
Burn Down
Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task Hrs | [10 empty] | <manually updated from total remaining time
Available Hrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <automatically generated from C3*C4*C5